## Project Journal
Date | Sprint | Planned Tasks | Actual Work Done
27th April 2019 | Sprint 0 | Overall Planning | Created tasks and deadlines for project completion
28th April 2019 | Sprint 0 | Dicussion on API distribution | Assigned owners to APIs
29th April 2019 | Sprint 0 | Decision on technology to implement APIs | Considered react and java
30th April 2019 | Sprint 0 | Decision on tasks for extra credit | Decided to go with deployment in EC2 cluster to container
1st May 2019 | Sprint 0 | Learn about cloud deployment | Spent some time to learn about cloud deployments and divided the deployment tasks among the team
2nd May 2019 | Sprint 0 | Intial Setup | Setting up a Node.js Express server for React
3rd May 2019 | Sprint 0 | MYSQL cloud setup | Created a RDS instance
4th May 2019 | Sprint 1 | Create APIs with basic functionality | Created APIs structure
5th May 2019 | Sprint 1 | Complete API functionality | Added API functionality
6th May 2019 | Sprint 1 | Adding validations to APIs | Added validations to APIs on the data recieved
7th May 2019 | Sprint 1 | Unit Testing and bug fixing | Unit testing and bug fixing
8th May 2019 | Sprint 1 | Deployment in cloud | Deployed in EC2 cluster and AWS container
9th May 2019 | Sprint 1 | Testing the application | Tested all the APIs with postman
10th May 2019 | Sprint 1 | Documentation of the project | Documentation of the project with recorded milestones

## Weekly Scrum Report
Week | Team member | What tasks did I work on / complete? | What am I planning to work on next? | What tasks are blocked waiting on another team member?
Week 1 | Akhila Sanka | 1. Planning 2. Picked API 3. Decided on technology implementation 4. Decided on cloud deployment options | 1. Manage order API 2. AWS container cloud deployment | Initial Node application setup
Week 1 | Sravanthi Bagani | 1. Planning 2. Picked API 3. Decided on technology implementation 4. Decided on cloud deployment options | 1. Signup API 2. Login API | Initial Node application setup
Week 1 | Vibhashree Ravindra | 1. Planning 2. Picked API 3. Decided on technology implementation 4. Decided on cloud deployment options | 1. Add Card API 2. EC2 deployment with auto scaling and load balancer | Initial Node application setup
Week 1 | Swetha Suresh | 1. Planning 2. Picked API 3. Decided on technology implementation 4. Decided on cloud deployment options | 1. Initial Setup of express-node app 2. RDS cloud setup 3. Payment API | None
Week 2 | Akhila Sanka | 1. Manage order API 2. AWS container cloud deployment 3. Documentation | None | None
Week 2 | Sravanthi Bagani | 1. Signup API 2. Login API 3. Documentation | None | None
Week 2 | Vibhashree Ravindra | 1. Add Card API 2. EC2 deployment with auto scaling and load balancer 3. Documentation | None | None
Week 2 | Swetha Suresh | 1. Initial Setup of express-node app 2. RDS cloud setup 3. Payment API 4. Documentation | None | None

## Individual Contributions
Individual Contributions
Team Member | Contributions
Sravanthi Bagani | Signup API
Signin API
Vibhashree Ravindra | Add Card API
Deployment in EC2 cluster
Swetha Suresh | Payment API
RDS instance setup
Intial Node-express app setup
Akhila Sanka | Manage Orders API
AWS container deployment

## XP Core Values
Value | Steps taken to have the values in project
Communication | 1. Using appropriate tools for communication
2. Transparency in actions/tasks performed
Simplicity | 1. Clarity of roles and responsibilities
2. Frequent Meetings (sprint meetings)
Feedback | 1. Contrustive feedback
2. Not waiting till the end to provide feedback
3. Encourage two-way feedback
4. Retrospective meetings
Respect | 1. Discussing with the other team members before taking a decision
2. Encourage team members to express opinions and ideas.
3. Include all team members in meetings & discussions.

## Task tracking
|  |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
Task | Task Owner | Initial Estimate (In Hours) | Week 1 - 04/27/19 | Week 1 - 04/28/19 | Week 1 - 04/29/19 | Week 1 - 04/30/19 | Week 1 - 05/01/19 | Week 1 - 05/02/19 | Week 1 - 05/03/19 | Week 2 - 05/04/19 | Week 2 - 05/05/19 | Week 2 - 05/06/19 | Week 2 - 05/07/19 | Week 2 - 05/08/19 | Week 2 - 05/09/19 | Week 2 - 05/10/19
Overall Planning | Team | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dicussion on API distribution | Team | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decision on technology to implement APIs | Team | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decision on tasks for extra credit | Team | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Learn about cloud deployment | Team | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Intial Setup | Swetha Suresh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
MYSQL cloud setup | Swetha Suresh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Signup API | Sravanthi Bagani | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0
Login API | Sravanthi Bagani | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Add Cards API | Vibhashree Ravindra | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1.5 | 0.5 | 0 | 0
Payments API | Swetha Suresh | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2.5 | 0.5 | 0 | 0
Manage Orders API | Akhila Sanka | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 2.5 | 1 | 0.5 | 0 | 0
Unit Testing and bug fixing - Signup API | Sravanthi Bagani | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Unit Testing and bug fixing - Login API | Sravanthi Bagani | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Unit Testing and bug fixing - Add Cards API | Vibhashree Ravindra | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Unit Testing and bug fixing - Payments API | Swetha Suresh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Unit Testing and bug fixing - Manage Orders API | Akhila Sanka | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Deployment in cloud - EC2 Auto Scaling with Load Balancer | Vibhashree Ravindra | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
Deployment in cloud - AWS Container (ECS) | Akhila Sanka | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
Testing the application | Team | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
Documentation of the project | Team | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 0
Remaining Hrs (Total) |  | 50 | 48 | 47 | 47 | 46.5 | 44 | 42 | 41 | 38 | 33.5 | 28.5 | 24 | 15.5 | 2.5 | 0
Ideal Burndown |  | 50 | 46.5 | 43 | 39.5 | 36 | 32.5 | 29 | 25.5 | 22 | 18.5 | 15 | 11.5 | 8 | 4.5 | 0